## Slide 1
PMS 2.0
01
Connected work. Verified completion.
Task management enhancement proposal
Management discussion
9 September 2026
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Presenter opening: We need a shared view of execution that tells us which work can start, which outputs we can trust and what threatens customer delivery.

## Slide 2
Management decision
02
Approve a pilot
Test connected handoffs for one machine family across purchases, stores and assembly.
Assign process owners
Agree readiness rules, completion evidence and escalation responsibilities.
Release funding in stages
Confirm scope and cost after workflow mapping, then expand only on pilot evidence.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Ask management for a bounded pilot and named owners. This proposal does not establish a development budget or committed delivery date.

## Slide 3
The current reporting gap
03
Isolated tasks
Departments work independently, according to the operational concern raised.
Unclear causes
A missed task date does not identify dependency waiting or execution overrun.
Uncertain completion
A status update may not prove that the next department can proceed.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. These are user-reported concerns, not quantified findings from production telemetry. Explain that the current task delay metric can still be correct as date variance while being incomplete for accountability.

## Slide 4
Existing code provides useful foundations
04
Area | Observed in repository | PMS 2.0 direction
Scheduling | Predecessor-based date logic | Validate actual readiness across departments
Completion | History of completion changes | Define evidence and acceptance rules
Assembly | Progress and sequence records | Link operations to material readiness
Code evidence does not establish live deployment or consistent adoption.
Notes: Repository sources: application/controllers/Task.php:10957; Database/task_completion_control_001.sql; Database/assembly_line_progress_001.sql; Database/assembly_machine_sequence_001.sql. A focused code review establishes existence of these elements only. Deployment, use, coverage and integration remain unverified.

## Slide 5
One shared plan for each order
05
Order and machine
Delivery commitment, accountable coordinator and forecast completion.
Operations and material
Work packages linked to the applicable BOM revision and material quantities.
Department actions
Each task has an owner, prerequisites and an accepted output.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Explain the hierarchy: order, machine, work package or operation, tasks and material requirements. Keep standalone administrative tasks outside unnecessary manufacturing dependencies.

## Slide 6
The operating model changes at each handoff
06
Today: reported concern | Proposed PMS 2.0 behavior
Tasks progress independently | Readiness reflects actual prerequisites
Task date drives delay reporting | Separate waiting, execution and delivery variance
Users mark completion | Transactions and acceptance establish completion
Departments follow separate lists | One order plan shows the next responsible action
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. This comparison represents the reported operating problem and proposed controls. It is not a claim that all existing code lacks these capabilities.

## Slide 7
Dependencies follow the real process
07
Sequential work
An operation waits for the accepted output of its predecessor.
Parallel work
Independent operations continue while unrelated activities remain open.
Several prerequisites
A stage becomes eligible only when all mandatory inputs are satisfied.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Reference: PMI Practice Standard for Scheduling, https://www.pmi.org/-/media/pmi/documents/public/pdf/certifications/practice-standard-scheduling.pdf . Dependencies, baseline comparison and critical-path principles inform the recommendation. No external benchmark or savings claim. Avoid one universal finish-to-start chain. Initial scope should use clear prerequisite rules and operation-level material gates. Validate workflow cycles and missing predecessors before release.

## Slide 8
Purchases and stores share material status
08
Step | Evidence | Downstream meaning
PO release | Approved PO and committed date | Material ordered
Goods receipt | Actual received quantity | Material physically received
Inspection, where required | Accepted and rejected quantities | Usable quantity known
Reservation and issue | Allocation to order and issue record | Material assigned to the operation
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. A PO is not receipt evidence. Receipt alone does not establish usability. Define inspection applicability by material class. Supplier promises and actual event timestamps are separate fields.

## Slide 9
Assembly readiness is specific to an operation
09
Required inputs
Approved drawing revision and the accepted material quantity for this stage.
Execution capacity
An available line and suitably skilled people support the planned start.
Receipt acceptance
Assembly acknowledges the issued kit and reports discrepancies.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Logical eligibility and capacity scheduling are distinct. Display material-ready work separately from capacity-constrained work. Do not wait for every component of the whole machine when the current operation can safely proceed.

## Slide 10
Partial supply can release useful work
10
Illustrative material status | Operation decision
Mechanical kit complete | Mechanical assembly can become ready
Control panel components incomplete | Electrical assembly remains blocked
Final-test component outstanding | Show testing risk without blocking unrelated work
Shared stock reserved to another order | Do not count it as available for this order
Readiness uses required quantities and allocation, not overall receipt percentage.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Illustrative scenario only. No actual material or order data. Calculate readiness from accepted, allocated quantities and valid revisions. Review substitutions through an authorized change process.

## Slide 11
Task states make work eligibility visible
11
State | Meaning
Planned / Ready | Future work / mandatory prerequisites satisfied
In progress / Blocked | Execution started / a recorded obstacle prevents progress
Submitted for verification | Owner reports completion with required evidence
Verified complete / Reopened | Output accepted / later issue requires further action
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. On hold represents an authorized suspension, distinct from a factual blocker. Keep transition timestamps. Reject invalid transitions. Reopening should re-evaluate affected successors and flag work already started.

## Slide 12
Completion requires an accepted output
12
Transaction evidence
Use receipts, inspection results, issues and operation records already captured.
Proportionate verification
Automate routine checks and reserve human acceptance for important gates.
Traceable correction
Record rejection, reopening, reason, actor and timestamp without erasing history.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Photos and remarks supplement evidence. They cannot replace quantity checks or quality acceptance. Define verifier roles and time limits so verification does not create a new bottleneck.

## Slide 13
Delay reporting separates different causes
13
Measure | Management question
Baseline variance | How far did the task move from the approved plan?
Dependency waiting | How long did a missing input prevent eligible progress?
Ready queue time | How long did ready work wait for execution?
Execution overrun | How much did execution exceed its agreed allowance?
Verification waiting | How long has acceptance remained pending?
Delivery variance remains a separate order-level measure.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Reference: PMI Practice Standard for Scheduling, https://www.pmi.org/-/media/pmi/documents/public/pdf/certifications/practice-standard-scheduling.pdf . Dependencies, baseline comparison and critical-path principles inform the recommendation. No external benchmark or savings claim. Use working calendars, defined interval boundaries and event timestamps. Measure blocker intervals without counting overlapping time twice. Report cause categories separately from total elapsed time.

## Slide 14
One disruption can affect several task dates
14
Illustrative sequence | Baseline | Actual
Required material ready | End of Day 2 | End of Day 5
Assembly: 2 working days | Days 3–4 | Days 6–7
Assembly completion | End of Day 4 | End of Day 7
Material readiness is 3 days late. Assembly execution overrun is 0 days.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Illustrative calculation assumes consecutive working days, assembly starts the next day, no other blockers and no scheduling flexibility. Material readiness moves 3 working days. Assembly duration remains 2 working days.

## Slide 15
Delivery impact depends on the remaining plan
15
Shared disruption
The same 3-day shift can appear against both material and assembly dates.
No duplicate project delay
Adding these task variances would incorrectly produce 6 days.
Conditional delivery impact
Delivery moves 3 days only if the plan cannot absorb or recover the shift.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Reference: PMI Practice Standard for Scheduling, https://www.pmi.org/-/media/pmi/documents/public/pdf/certifications/practice-standard-scheduling.pdf . Dependencies, baseline comparison and critical-path principles inform the recommendation. No external benchmark or savings claim. Use the preceding example. The critical path is the sequence that governs completion. Capacity, calendars and remaining work also affect the forecast. Do not infer order delay by summing overdue task days.

## Slide 16
The baseline stays visible as forecasts change
16
Approved baseline
Retain original milestone dates and their approval history.
Current forecast
Recalculate likely dates using verified progress and remaining constraints.
Controlled replan
Record why a plan changed and who authorized a new baseline version.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Reference: PMI Practice Standard for Scheduling, https://www.pmi.org/-/media/pmi/documents/public/pdf/certifications/practice-standard-scheduling.pdf . Dependencies, baseline comparison and critical-path principles inform the recommendation. No external benchmark or savings claim. Automatic date movement must not overwrite the original commitment. Show baseline, current forecast and actual dates together. Distinguish customer commitment changes from internal recovery plans.

## Slide 17
Every blocker has a resolver and a next action
17
Record | Purpose
Cause and affected operation | Explain what cannot proceed and why
Resolver and target date | Name the person responsible for removing the obstacle
Evidence and time interval | Support a reviewable delay explanation
Escalation and recovery action | Make overdue or delivery-critical blockers actionable
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Proposed cause categories: supplier delay, shortage, drawing clarification, inspection rejection, capacity constraint, customer change and execution issue. Assignment does not automatically establish fault. Require review of contested attribution.

## Slide 18
Ownership covers both tasks and handoffs
18
Role | Proposed accountability
Order coordinator | Overall plan, cross-department issues and forecast
Purchases owner | Supplier commitment and material follow-up
Stores / quality owner | Receipt, acceptance, allocation and issue accuracy
Assembly owner | Kit acknowledgement and operation execution
Process owner / manager | Exceptions, disputed causes and overdue acceptance
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Role assignments are proposed and require management confirmation. Where quality is a separate department, it owns inspection acceptance. Each gate should have one accountable role and a clear backup.

## Slide 19
Management sees the orders that need intervention
19
View | Decision supported
Delivery risk | Which orders need recovery action?
Material blockers | Which shortage should purchases resolve first?
Ready work awaiting capacity | Where can line or manpower changes help?
Unverified completion | Which handoff needs acceptance?
Reopened work | Where do recurring quality failures need attention?
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Proposed dashboard content, not a live dashboard or actual KPI result. Prioritize exceptions by delivery impact and age. Provide drill-down to order, operation, evidence and responsible resolver.

## Slide 20
Pilot measures make improvement testable
20
Metric | Definition
On-time delivery | Orders completed by commitment / completed orders
Blocked time | Working time in validated blocker intervals
Ready queue time | Working time from readiness to execution start
Verification time | Time from submission to acceptance
Reopen rate | Completed tasks reopened / completed tasks
Baseline values and numerical improvement targets remain to be agreed.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Choose a common cohort and measurement window. Define treatment of cancellations, approved date changes and multiple reopenings. Compare like machine families and order complexity. Report medians and upper-tail times when volumes permit.

## Slide 21
Software changes connect existing business events
21
Shared identifiers
Link order, machine, BOM revision, operation and material line across modules.
Rules and event history
Store dependencies, state transitions, evidence and blocker intervals.
Reliable integration
Validate quantities, prevent duplicate events and reconcile missing updates.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Proposed design requires detailed discovery. Include permissions, immutable audit events, retry handling, stock reconciliation and revision control. Keep historical records intact. Do not claim the current system already has these integrations.

## Slide 22
A phased rollout limits disruption
22
Phase | Scope | Exit evidence
1. Agree the process | Map one machine family and approve gate rules | Owners sign off on scenarios
2. Build and pilot | Connect events, readiness, verification and blockers | Live records reconcile with actual work
3. Improve and expand | Add capacity forecasts and more machine families | Pilot measures justify wider rollout
Pilot scenarios include partial receipt, rejection, shortage, rework and late handoff.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. This is sequencing, not a committed schedule. Estimate effort, dependencies, cost and dates after discovery. Use a limited transition period and define which system owns each field.

## Slide 23
Benefits require baseline evidence
23
Value hypothesis | How to test it
Less assembly waiting | Compare waiting hours for similar operations
Less manual follow-up | Measure coordination time per order
Fewer false completions | Review rejected and reopened handoffs
More reliable delivery forecasts | Compare forecast dates with actual completion
No savings percentage, ROI or development budget has been assumed.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Financial model, if required: avoided waiting hours times applicable avoidable cost per hour, plus coordination hours saved times loaded hourly cost, less implementation and ongoing cost. Do not equate all time saved with cash savings. Avoid double counting labor and waiting benefits.

## Slide 24
Evidence and assumptions
24
Known from operations
The PMS owner reports independent department work and uncertain completion.
Observed in code
Scheduling, completion history and assembly progress elements exist. Live coverage needs confirmation.
Proposed and unmeasured
Workflow rules, role assignments and pilot metrics need validation with department owners.
Reference: PMI Practice Standard for Scheduling. Full source details are in notes.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Repository references: application/controllers/Task.php:10957 and :11666; Database/task_completion_control_001.sql; Database/assembly_line_progress_001.sql; Database/assembly_machine_sequence_001.sql. Scheduling source: Reference: PMI Practice Standard for Scheduling, https://www.pmi.org/-/media/pmi/documents/public/pdf/certifications/practice-standard-scheduling.pdf . Dependencies, baseline comparison and critical-path principles inform the recommendation. No external benchmark or savings claim. All numerical examples are illustrative. This presentation is a proposal based on a focused review, not a production audit.

## Slide 25
Approval requested
25
A bounded pilot for one machine family
Management sponsor and department owners
Agreed readiness and completion rules
Discovery to confirm effort, cost and delivery plan
Pilot review before wider rollout
Success means reliable handoffs and a credible delivery forecast.
Notes: Source: PMS owner description in this conversation, 9 September 2026. Proposed future state unless explicitly stated otherwise. Close by asking management to approve the pilot scope, name the sponsor and process owners, authorize discovery to establish effort and cost, and set a review gate before wider rollout. Do not imply approval has already occurred.